Part 610 - UPDATING SOIL SURVEYS

Table of Contents

PART	TITLE	PAGE

610.00 Definition and Purpose.	610-1

610.01 Policy and Responsibilities.	610-1

610.02 Workflow for Updating Soil Survey by Major Land Resource Area.	610-3

610.03 Evaluating Deficiencies to be Corrected in Soil Survey Updates.	610-6

610.04 Developing and Implementing Plans for Updating Soil Survey Information.	610-8

610.05 NASIS Legend Management for Updates.	610-11

610.06 Managing Soil Spatial and Tabular Databases.	610-12

610.07 Certification of Soils Data.	610-14

Exhibit 610-1 Sample Map Unit Evaluation Worksheet.	610-17

Exhibit 610-2 Sample Evaluation Information for Long-Range Planning.	610-19

Exhibit 610-3 Example of a Soil Survey Update Implementation Guide	610-21

Part 610 - UPDATING SOIL SURVEYS

610.00 Definition and Purpose.

- Updating of soil survey information is the continuous activity of data collection, reviews, evaluations, and additions to existing soil survey information.

- Updating soil survey information ensures that current and accurate seamless soil survey information is available to meet the needs of the majority of users.

- MLRA soil survey update projects are planned and organized to focus on specific groups of soils and their associated support data and interpretations (see part 608.04).

- Update projects are generally coordinated across the existing (i.e. “traditional” or Non-MLRA) soil survey area boundaries and follow natural landforms.

610.01 Policy and Responsibilities.

- Policy.

  - Soil survey update activities are conducted as a series of prioritized projects that are agreed upon by the Soil Survey Area Management Team.  Projects are developed in the context of the entire MLRA Soil Survey Area.

  - Analysis and update is by MLRA Soil Survey Area, stored in NASIS, and delivered through the Soil Data Mart as county, parish, or other subsets.

  - Correlation decisions are recorded in NASIS or, if not yet SSURGO-certified, with an amendment to the correlation document, as appropriate.

  - Update projects are generally based on associated soils on natural landforms over a broad physiographic area. Maps and data are brought to a consistent level with joined data and soil delineations that follow natural landforms. The maps and data are also coordinated across the original existing soil survey area boundaries (i.e. county, parish, etc.).

  - Extensively updating the mapping of a previously published soil survey area (e.g., county- or parish-based) can be proposed by the Soil Survey Area Management Team as a project. However, it requires permission from the Soil Survey Division Director. If approved, it must be done within the context of the larger MLRA Soil Survey Area.

  - The MLRA Soil Survey Area long-range plan lists major items required to bring the existing soil surveys in the area to the standard defined by the MLRA Region-wide memorandum of understanding.  The plan is based in part on evaluations completed under the direction of the State Soil Scientists for each of the Non-MLRA soil survey areas in the region. The long range plan is developed by the coordinated efforts of the MLRA Soil Survey Technical Team and the MLRA Soil Survey Area Management Team (see parts 608.05 and 608.06).  Exhibit 608-3 illustrates an example of needs compiled in a long-range plan for a MLRA Soil Survey Area.

  - Priorities are established by the MLRA Soil Survey Area Management Team.  Project plans are developed by the MLRA Soil Survey Area Technical Team see part 608.04. Annual plans of operation are developed to guide and provide specific focus to the MLRA Soil Survey Area staff.  Goals and progress reporting reflect the details in the annual plan.

  - Official soil survey attribute data, and to the extent possible, all other official soil survey information (maps, interpretations, and metadata) are maintained in a central, sole-source repository (Soil Data Warehouse) and accessible electronically through various soil data marts.  Official soil survey information (maps, data, interpretations, and metadata) is identified in the Field Office Technical Guide.

  - Proposed revisions, modifications, and supplemental mapping are documented and, when determined appropriate by an evaluation of the soil survey, used to revise the official soil survey information.  Revisions, modifications, supplemental mapping, or remapping require evaluation actions listed in 610.03.

  - Bring soil survey maps and data up-to-date within the MLRA Soil Survey Area.  Ensure that maps have common soil polygon lines and features and share basic soil properties and selected soil qualities (see Exhibit 609-2).

  - Coordinate and utilize common standards for updating soil survey information within the MLRA Soil Survey Area with those established and defined in the MLRA Region-wide memorandum of understanding (see part 606 for information on MOU’s).  Specific details can be included in the long-range plan and the project plans as needed.

  - Use a common map scale, map unit symbol, map unit name, map unit design, and mapping intensity within broad physiographic areas to provide soil information at a level commensurate with most user needs.

  - All revisions to soil survey information are developed within the context of the overall MLRA Soil Survey Area.

- Responsibilities.

Primary responsibility for various aspects of updating soil surveys is with state offices, MLRA Soil Survey Regional Offices (MO), MLRA Soil Survey Offices (MLRA SSO), and on some federal lands the NCSS partner agencies.  The General Manual, Title 430, Part 402, Subpart B, outlines responsibilities of these offices and other soil survey business areas.  In addition to the following responsibilities, refer to part 608.01 for a partial overview of responsibilities.

  - MLRA Soil Survey Regional Offices (MO)

    - the MLRA Soil Survey Regional Office Leader participates as a member of the MLRA Management Team to review the long-range plan and set priorities;

    - provides guidance to the MLRA Soil Survey Office in initiating and carrying out the process of updating soil survey information;

    - assures the quality of all new and revised soil survey data in the region;

    - conducts a quality assurance review of the revised spatial data;

    - manages the assignment of editing permissions in NASIS and assures that individuals with editing privileges are properly trained; and

    - approves changes to the legend that are proposed by the MLRA Soil Survey Office.

  - State Offices
As program managers, state soil scientists:

    - are responsible for assuring that evaluations of Non-MLRA soil survey areas within their state are conducted to identify deficiencies, problems, and needs. These may be conducted by members of their staff, by the MLRA soil survey area technical team, or a combination of both as deemed necessary and appropriate;

    - lead the MLRA Management Team for MLRA Soil Survey Offices located in their state;

    - participate in MLRA Management Teams for MLRA Soil Survey Offices serving their state but located in adjoining states;

    - in cooperation with the Management Team members, develop priorities for soil survey update projects;

    - inform State Conservationists and where applicable, leaders in partner agencies, of the project plans to be carried out by MLRA Soil Survey Offices and obtain concurrence; and

    - provide administrative management activities for the MLRA Soil Surveys Offices located in their state.

  - MLRA Soil Survey Offices (MLRA SSO)

    - lead the MLRA Technical Team and carry out its functions;

    - follow the guidance provided by the MLRA Soil Survey Regional Office in initiating and carrying out the process of updating soil survey information;

    - develop a long range plan incorporating information from completed evaluations of Non-MLRA soil survey areas.

    - develop project plans for approval by the MLRA Management Team;

    - develop, manage, and update all map unit information;

    - propose changes to the legend, such as component names used in the map unit name;

    - correct errors, obsolete terms, and null data;

    - inform the MO of work being performed by them on the database;

    - analyze the official soil survey legends of the MLRA and reconcile the map unit names in order to prepare a legend for the MLRA or for some portion thereof;

    - compile a list of map unit names for the broad update area to facilitate the correlation of map units among individual soil survey areas within the area.  Uniformly named map units and a consistent symbol legend enhance usability; and

    - update all data map units when combining map units during correlation.

610.02 Workflow for Updating Soil Surveys by Major Land Resource Area.

The MLRA Soil Survey Regional Offices are responsible for providing guidance to MLRA Soil Survey Offices for implementing a soil survey update process.  Exhibit 610-3 is an example of an implementation guide developed by a MLRA Soil Survey Regional Office.  Soil survey needs, as well as strategies to achieve needed enhancements vary across the nation.  A common approach that can be used includes: a) evaluating existing soil survey information; b) identifying deficiencies to be corrected; and then; c) developing and implementing plans to update the area. The following outline presents the major information items to be considered in updating soil surveys for an MLRA Soil Survey Area.

- Evaluation of existing soil surveys.

  - A general evaluation of existing soil surveys and an identification of deficiencies needs to be included as part of the long-range plan. This evaluation will include items such as:

    - review of legends;

    - examination of the geographic distribution of soils using GIS tools;

    - examination of spatial data for join problems; and

    - gathering known information about the quality of existing soil surveys from Resource Soil Scientists, Conservationists, other discipline specialists, and other knowledgeable sources.

  - Inventory and review of benchmark soils

    - current status and need for revision;

    - inventory of existing data; and

    - identification of data gaps.

  - Review and update of official soil series descriptions (OSD)

    - georeferenced;

    - metric units of measure;

    - use of current taxonomy and horizon designations;

    - competing series;

    - distribution and extent;

    - diagnostic horizons and features; and

    - other items needing attention.

  - Taxonomic classification of soil components

    - apply latest edition of the Keys to Soil Taxonomy.

  - NASIS database review.

    - integrity and management of site and legend objects;

    - unique map unit names within the MLRA soil survey area;

    - typical pedon selection;

    - consistent use of data population guides and calculations; and

    - other items needing attention.

  - Spatial database review.

    - correction of symbol errors due to recompilation;

    - adjustment of line placement errors; and

    - other items needing attention.

  - Gathering and organizing existing data.

    - Soil Surveys in the MLRA Soil Survey Area

      - Previously completed soil surveys

      - Soil surveys for conservation planning

      - Soil survey quality control data, including field notes and documentation

      - Soil survey photographs, block diagrams, and other figures

      - Soil survey quality assurance documents

      - Soil correlation memoranda and amendments

    - Reference Maps (use in digital format if available)

      - Original field sheets

      - Major land resource area maps

      - General soil map

      - All available aerial photography and other remote sensing coverage

      - U.S.G.S. topographic and slope maps

      - Public lands survey

      - Maps and text on geology, geomorphology, geography, and water resources

      - Maps and text on vegetation and land use

      - Climatic maps and data

      - Flood plain maps

      - Maps and text on air resources

      - U.S. Fish and Wildlife Service wetland maps

    - Reports and Inventories

      - Census reports

      - Crop reporting service reports

      - Multi-spectral data

      - River basin reports

      - State, regional, or county land use plans and regulations

      - RC&D work plans

      - Public lands management reports and inventories

      - Bulletins and reports of State Agricultural Experiment Stations

      - National Food Security Act Manual and similar manuals

      - National resource inventory data

      - Field office technical guides

      - Soil laboratory data

    - Scientific and Research Reports and Data

      - Theses and dissertations of college or university students

      - International committee (ICOM) reports - e.g. wet soils, Vertisols, Aridisols, Andisols

      - Articles in scientific and technical journals

      - Well logs from local or state agencies

      - NRCS drainage, irrigation, and erosion control guides and maps

      - Percolation test results from local agencies

      - Highway soil test data

      - Climate data

      - Geomorphology studies

    - Forestry, Range, and Wildlife Inventories and Studies

    - Forest inventories

      - Range inventories

      - Studies and reports on wildlife habitat recreational sites

    - Official Soil Series

      - Current version of official soil series descriptions (OSD)

      - Archived copies of previous versions of official soil series descriptions (if available)

    - Databases

      - National Soil Information System (NASIS) database

      - U.S. General Soil Map (STATSGO2) database

      - Soil Survey Geographic (SSURGO) database

      - Soil Characterization databases (NRCS and Universities)

    - Digital Data

      - Digital orthophotography

      - Digital raster graphic

      - Digital elevation model

      - Common land units

      - Common Resource Areas

      - Digital hydrography, transportation, etc.

- Evaluating deficiencies to be corrected in soil survey updates.

See part 610.03 for more information on the evaluation process used for identifying deficiencies.

- Developing and implementing plans for updating soil survey information.

See part 610.04 for more information on these phases of updating soil surveys.

610.03 Evaluating Deficiencies to be Corrected in Soil Survey Updates.

Each official Non-MLRA soil survey area is evaluated within the context of the greater MLRA Soil Survey Area for update needs.  The goal is to inventory the work required to bring all soil survey areas within the MLRA soil survey area to a common, coordinated standard. The individual evaluations will be integrated into a long range plan for the MLRA soil survey area. The state soil scientist provides the leadership in assessing the needs for each of the existing soil surveys in the state. The evaluations may be conducted by their staff, the MLRA soil survey technical team, or a combination of both as deemed necessary and appropriate.

The extent of the evaluations will depend on the current level of existing knowledge about each soil survey.  For many soil survey areas, some knowledge is available from staff experience, records, or from those who participated in the previous soil survey.  Users of a given soil survey may have kept records of deficiencies.  In most instances, existing information on deficiencies is available and an abbreviated evaluation process is all that is needed.  Only where information is limited, is a more structured evaluation required.  In either case, the result of evaluations summarizing deficiencies and recommendations for improvement is documented in the Long-Range Plan.  The evaluation worksheet in Exhibit 610-1 is useful for soil surveys that have little or no information available to current staff.  However, the preferred method is to record evaluations in the NASIS database.  See part 610.03 (d) for more information.

- Overview of the Evaluation Process.

Prior to any soil survey updating activity, an evaluation of the overall condition of the original survey areas is required.  Evaluation of all soil survey areas within an MLRA should be done within a relatively short period (1 year or less), utilizing a consistent format.  Evaluations include three major components:

  - Customer needs.

Determine the current and projected user requirements and needs.  The original soil survey memorandum of understanding records user needs and specifications for the survey at the time it was initiated and can be helpful in assessing the likely needs for update.

  - Databases.

The spatial and attribute databases are evaluated in the context of the published manuscript.  The published manuscript contains the map unit concept and the map unit delineations at the point in time the survey mapping was completed or officially correlated.  The databases should be evaluated to identify issues such as proper line placement, quality and completeness of soil property data, and current soil interpretations.

  - Interpretations.

Soil interpretations are evaluated with consideration given to the current and projected needs of the survey.  The types of interpretations needed for the survey area and the soil properties needed to generate the interpretations are considered during the evaluation process.

- Responsibilities and Coordination of Evaluations.

The State Soil Scientist provides leadership and direction to the evaluation process within their respective state.  The State Soil Scientist assures that the evaluation includes documentation related to the current quantity and quality of the soil survey data.  This evaluation serves as an inventory and assessment of each Non-MLRA soil survey area. The evaluations are provided to the MLRA-SSO for integration into a long range plan.

- Evaluation Process.

The process for evaluating soil surveys will vary somewhat across the nation depending on the age of soil surveys represented, order(s) they were conducted at, and other factors. The following outline provides an example of basic steps to be carried out in the evaluation process.

  - Assemble, review, and summarize the existing documentation on file.

    - map unit descriptions in published manuscripts

    - unpublished soil information

    - records documenting soil survey joining problems

    - interpretations

    - correlation records

    - field review reports

    - special investigation and laboratory data

    - pedon descriptions

    - transect data

    - tacit knowledge of those experienced in the area

    - notes of needed changes recorded in the office copy of the published soil survey

  - Some examples of items to be considered when evaluating a soil survey include:

    - soil delineations conform to landform positions

    - appropriate level of detail

    - adequacy of the imagery

    - land use change

    - map unit design/composition

    - taxonomic classification

    - need for laboratory or other support data

    - adequacy of the database to support interpretations

  - Interview users of the data including NCSS cooperators, state and local government agencies, NRCS field office staff, Resource Soil Scientists, and Soil Scientists who worked in the survey area or in adjacent survey areas.

  - Look for variability of soil delineations which may result from individuals’ mapping style, differences in detail within and among soil survey areas, and the consistent use of spot symbols.

  - Evaluate the validity and regional consistency of application of map unit concepts:

    - Analyze the soil-landscape model:  Do the same map units occur in the same or similar geology, landforms, and parent materials?

    - Are lines placed accurately on the map?  Do crisp boundaries exist where these placements may be evaluated, e.g., the upland and flood plain interface or at the edge of water features?

  - What are the join issues between adjacent soil survey areas?

  - What is the extent of change in land use within the survey area?

  - Have catastrophic natural events or human activities altered the land?

  - Review the kind and accuracy of the soil interpretations.  Consider interpretive results and relation of data entries to criteria:

    - interpretations that were not previously included, and are currently needed, and the development of local interpretations;

    - improvements that can be made by new and improved data;

    - changes in land use since the base photography was acquired;

    - the need for additional soil property or soil quality information;

    - knowledge of soil response to different uses and management.

  - Review and evaluate the accuracy and consistency of data that exists in NASIS.

- Evaluation Documentation

All evaluation notes are entered into NASIS Legend text and Mapunit Text tables.  Information on map units is entered in the NASIS Mapunit Text table using the Kind set to “miscellaneous notes”, the category set to “evaluation” and the subcategory set to “spatial”, “attribute”, or “interpretation”.  The NASIS national report named “MLRA -mgmt- Survey Evaluation notes for long-range planning” compiles the evaluation notes for each Non-MLRA soil survey area legend and the report can then be used to help write a long-range plan.  The report output is used as a tool in the decision making process for the survey areas within the MLRA Soil Survey Office territory.  A written summary of the evaluation must be a component of the process to allow development of conclusions and a comparison of situations among survey areas within an MLRA.  The evaluation worksheet in Exhibit 610-1 and sample evaluation report in Exhibit 610-2 can be used as guides for populating evaluation notes in NASIS.  Modify them to accommodate local conditions.

610.04 Developing and Implementing Plans for Updating Soil Survey Information.

Actions to update soil survey information are based on the results of the formal evaluations of the existing soil surveys. The information from these evaluations must be brought together and consolidated for the MLRA Soil Survey Area.  All update of soil survey information is planned and conducted within the context of the entire MLRA Soil Survey Area.  The state soil scientists for the states served by the MLRA Soil Survey Office, in cooperation with the lead scientists of cooperating  partners, the MLRA Soil Survey Regional Office leader, and the MLRA Soil Survey Office leader work with the above information to develop an inventory of needs for the MLRA Soil Survey Area. The MLRA Soil Survey Area Technical Team (see 608.05(c)) uses this information to develop the long-range plan for the MLRA Soil Survey Area. These needs are prioritized by the MLRA Management Team, and presented to the Board of Directors (or applicable subset of BOD members) for concurrence.  Projects plans are then developed by the MLRA Soil Survey Office Technical Team to address the highest priorities. A common approach is to focus on specific groups of soils within the MLRA soil survey area and coordinate them across existing soil survey area boundaries, following natural landforms.  Update of soil survey information includes soil tabular databases, soil spatial data, and documentation; such as information from soil investigations.

- Long-Range Plan

  - The long-range plan provides an inventory of all categories of soil survey work needed to bring the deficiencies identified in the evaluation to the standard defined in the MLRA region-wide memorandum of understanding.  Exhibit 608-3 illustrates an example of needs identified for an MLRA Soil Survey Area.

    - Identified needs for the MLRA Soil Survey Area are prioritized by the MLRA Soil Survey Area Management Team (Exhibit 608.4 provides an example of a ranking procedure that can be used) and reviewed by the Board of Directors (or applicable subset of members).

    - Archive a record of the complete list of needs in the long-range plan and use as a basis for formulating project plans for the MLRA.

  - The plan should include a strategy to update soil mapping.  Include a discussion of the categories that best describe the work needed to bring the soil maps to a common standard throughout the MLRA Soil Survey Area.  Use a planimetrically correct base to join adjacent surveys.  Support all revisions with a documented evaluation of the entire MLRA Soil Survey Area.  Plans to update soil mapping depend on the results of the formal evaluation.

    - Extensive revision (a detailed form of “update”)

Extensive revision requires considerable fieldwork involving remapping and updating soil descriptions.  Extensive revision is seldom used and available only if the survey evaluation documents that remapping a significant portion of the survey is justified.  Revising the soil map for a significant portion of an existing soil survey is rarely needed.  When such a revision is deemed necessary, use the same procedures as listed for an initial soil survey.  A project soil survey memorandum of understanding is not required, but can be prepared if it is deemed valuable.  It must be compatible with the MLRA Region-wide MOU.  Approval to extensively revise must be obtained from the Director of the Soil Survey Division.  Include the soil survey evaluation along with the request for approval.

    - Update

All other degrees of revision are included in “Update”.  A long-range plan is developed to establish update priorities within the MLRA soil survey area that accommodate all or most of the parties involved (e.g., different states, agencies, and partners).  One or more project plans describing the specific work and timeline are developed to address the highest priorities to be accomplished by the MLRA Soil Survey Office staff.  See part 608.04.

    - Modernize the soil map base

Obtain a new base and compile soil delineations, symbols, and cultural features only when the soil map base is not sufficiently current to meet the needs of the survey.  Digitize a new soil map and issue as needed.  Purchase of a new base requires approval by the Director, Soil Survey Division.  Send requests to the Director, National Soil Survey Center, for coordination.  This action is normal maintenance of the soil survey.  The status of soil survey continues as published in the Soil Survey Schedule.  A project soil survey memorandum of understanding is not required.

    - Supplemental soil mapping

Supplemental mapping is another soil data layer that is made for a specific purpose.  It provides more detailed soil information than is contained in the official soil survey for an area of limited extent, such as a university experiment station farm.  Document the objective, purpose, scale, and expected use of the information.  Map the area and record supporting data, such as the soil legend, map unit descriptions, soil properties and qualities, and interpretations.  Supplemental information is issued as needed on a local basis.  These actions, however, do not constitute a change to official soil survey information.  The status of soil survey continues as published in the Soil Survey Schedule.  A memorandum of understanding is not required.

  - Specify which method will be used to manage the MLRA Soil Survey Area legend (see part 610.05).

- Project Plan

  - Based on the prioritized inventory of needs in the long-range plan, identify specific high priorities within the MLRA Soil Survey Area to be developed into one or more project plans that can be completed in a timely manner (see part 608.04)..

  - The MLRA Soil Survey Office staff, in cooperation with the MLRA Soil Survey Area Technical Team (see 608.05(c)) develops one or more project plans detailing the work required to accomplish the agreed upon priorities (see Exhibit 608-5).  Plans should be developed in such a way that progress can be tracked and clear goals and milestones can be identified and assigned to staff members.  In addition, the projects must result in updating official soil survey information periodically so that improved information is provided to customers and progress can be reported.  The format and details of the plan will vary depending on the situation.  However, the preferred approach is to focus on specific groups of soils within the MLRA soil survey area and coordinate their spatial and tabular information across existing soil survey area boundaries, following natural landforms.

  - Soil survey investigations may be needed as part of project plans for the MLRA Soil Survey Area.  All investigations require that a research work plan be developed by the MLRA Soil Survey Office Leader in consultation with the MO, partner agencies, and assigned National Soil Survey Laboratory liaison who will assist the MLRA Soil Survey Office Leader through expert consultation and providing regional and national coordination of investigations.  See part 631 for more information on Soil Survey Investigations.  Exhibit 631-3 has a research work plan checklist and exhibit 631-4 is an example of a research work plan.

- Annual Plan of Operations

  - Annual plans of operation (sometimes called business plans) should also be developed to guide and provide specific focus to staff as the projects are being implemented.  These are developed each fiscal year and identify goals, objectives, timelines and responsibilities to guide the staff in planning day-to-day operations.  See part 608 for more information.

  - Annual plan of operations will be put in place by MOs and MLRA SSOs after MLRA project plans are developed .  The list of needs and priorities may change with time (Farm Bill priorities, deficiencies identified as other projects are being performed, cost share opportunities, etc.) and flexibility should be maintained to make adjustments within this process.

- Implementing Plans to Update the MLRA Soil Survey Area.

  - Organize the workload after developing the long-range, project, and annual plans described above.

  - Revise the spatial data.

    - Use GIS tools (such as Soil Data Viewer and ArcGIS), NASIS query functionality, landscape predictive models where available, and statistical analysis to summarize data in order to detect inconsistencies and anomalies to be addressed.

    - Field Investigations and data collection may be needed to collect data identified in the previous step. Sites are identified (preselected) during the data analysis phase and are statistically representative of the landscape and are large enough to sample.  Use GPS to navigate to the site and collect data, including vegetative data, as documentation.  Edit tabular and spatial data as appropriate.

  - Revise existing soil properties, qualities and interpretations.

    - Based on review of accuracy and consistency of data and interpretations in the database, revise as needed.

    - Populate missing data as appropriate.  See parts 618 and 638 for guidance.

    - Consider the need for new data elements and/or interpretations.

- Quality Control and Quality Assurance Activities.

  - The MLRA Soil Survey Office Leader is responsible for quality control of the soils information within the MLRA soil survey area.  The MLRA Soil Survey Office Leader reviews data online as well as conducting site visits throughout the area (see 609.04)

  - The MLRA Soil Survey Regional Office Leader is responsible for quality assurance of the soils information within the entire MO area of responsibility (see 609.05).  The MLRA Soil Survey Regional Office works closely with partner agencies on federal lands in carrying out quality assurance activities.

- Updating the Soil Data Warehouse and Soil Data Mart.

As project plans (or portions thereof) are completed, and NASIS data has been updated, the MLRA Soil Survey Regional Office staff completes a quality assurance review of the process and a technical review of the spatial and attribute data.  The State Soil Scientist is informed that the survey areas are complete and available for posting to the Soil Data Mart and to the Web Soil Survey.  This process allows for a timely delivery of updated soil survey data.

610.05 NASIS Legend Management for Updates.

Purpose

Managing legends in NASIS contributes to the overall goal of providing a seamless, high-quality soil survey geographic database (SSURGO) for the nation.  The major land resource area (MLRA) is the geographic area chosen to manage, update, and upgrade soil survey information.  Subsets of soil survey information – a traditional Non-MLRA Soil Survey Area, a Common Resource Area, a National Forest, or a watershed – can be clipped out using a GIS, and the associated attribute data could be selected using the legend area overlap NASIS query.  The MLRA Soil Survey Areas are designed to facilitate the update of soil survey information, either by map unit, groups of map units, series and groups of series, landform, and geographic area or other areas not coincident with the traditional soil survey areas.  The soil survey legend is a tool for the MLRA Soil Survey Office Leader to evaluate, manage, correlate, update, and upgrade the soil survey information within the geographic area of responsibility.

The “Non-MLRA Soil Survey Area” legends are designated as the Official Legend for the traditionally defined soil survey areas.  These legends are posted to the Soil Data Mart by the State Soil Scientist.  It is not necessary to create additional copies of the “Non-MLRA Soil Survey Area” legend for a survey area that is under update.  The map units and their documentation, correlation history, and progress are to be maintained in the one “official” legend.  The Soil Data Warehouse is the archive database for older versions of the legends and associated tabular and spatial data.

610.06 Managing Soil Spatial and Tabular Databases.

Official certified soil survey attribute data, and to the extent possible, all other soil survey information (maps, interpretations, and metadata) are maintained in a central, sole-source repository (Soil Data Warehouse).  These data are accessible to customers electronically through the Web Soil Survey and the Soil Data Mart, which are dynamic soil survey information delivery systems. SSURGO spatial, tabular, and metadata can also be obtained from the Geospatial Data Gateway. New and updated soil survey information, when placed into the Soil Data Warehouse, provides customers with the latest soil survey information.  Procedures to enhance the information in the Soil Data Warehouse are part of the normal update of soil survey information

Managing Tabular Data

Incorrect entries, obsolete terms, and null data are common deficiencies in the Soil Data Warehouse.  Data searches of these errors satisfy the need for an evaluation and change over the extent of the map unit and additional evaluation actions are not needed.  Entries or corrections to data entries can be made anytime that the errors are discovered, including changes to taxonomic soil classification.  Changes that affect the legend, such as component names used in the map unit name, are proposed by the MLRA SSO and approved by the MO.  Correlation decisions should be recorded in NASIS or, if not yet SSURGO-certified, with an amendment to the correlation document as appropriate.  The MO assures the quality of all new and revised soil survey data in the region.

- The MO assures the quality of all new and revised soil survey data in the region, conducts a quality assurance review of the revised spatial data, manages the assignment of editing permissions in NASIS, assures that individuals with editing privileges are properly trained, and approves changes to the legend that are proposed by the MLRA Soil Survey Office. The MO coordinates with the states to develop a plan that addresses the population of new data or correction of existing NASIS datasets.  The purpose of the plan is to minimize the risk of data being included that does not meet NCSS standards, that is inconsistent with data in adjoining areas of the same soils, and that is of unknown origin.  The plan builds quality control and quality assurance into the editing process.  The plan may include information such as:

    - a list of individuals who have permissions to edit the data;

    - actions to obtain needed training;

    - a list of data map units and data elements expected to be addressed;

    - guidance documents, algorithms, and other aids to be used; and

    - a schedule of when work will be done.

- The State Soil Scientist:

    - assigns competent, trained individuals within the state to edit data in NASIS as necessary to carry out program responsibilities;

    - informs the MO or work being performed on the database and requests edit privileges as needed; and

    - notifies the appropriate area and field offices, and affected partner agencies of significant revisions to the database.

Permissions to Edit Data

Entering new data and revising existing data may be done by MO staff, State Office staff, MLRA Soil Survey Office staff, or other appropriate individuals, as agreed to by the State Soil Scientist and MLRA Soil Survey Regional Office Leader.  NCSS partner agencies may be the steward for soil survey data on federal lands.  The State Soil Scientist may assign competent, trained individuals within the state to edit data in NASIS as necessary to carry out program responsibilities.  The MO is responsible for assigning editing permissions in NASIS and assuring that individuals with editing privileges are properly trained.  Allowing data to be edited at multiple levels in the organization facilitates improvements to the soil data and timely distribution to the public through the Soil Data Mart and Web Soil Survey.

- Scheduled Updates to the Data.

At least annually, and as frequently as needed to meet NRCS or cooperator needs, schedule updates to the information in NASIS and export to the Soil Data Warehouse for all soil survey areas.  Soil databases are maintained by the individual Non-MLRA Soil Survey Area defined within NASIS.  See Part 608.02 for information on soil survey area designation.

- Managing Spatial Data.

Use various GIS and database software to coordinate across multiple Non-MLRA Soil Survey Areas within the MLRA.  Use a planimetrically correct base to join adjacent surveys.  Support all revisions with a documented evaluation of the entire MLRA.

- Assemble a spatial dataset for the MLRA Soil Survey Area using an acceptable coordinate system, quality standards, portable format, and scale for all geographic areas for which the MLRA Soil Survey Office is responsible.

- Any part of the MLRA Soil Survey Area-wide dataset (as defined by an area-of-interest) can be extracted/exported for evaluation, editing, and/or updating.

- When work is completed, the revised spatial dataset from the area-of-interest is checked-in/merged with the MLRA Soil Survey Area-wide dataset for evaluation by the MLRA Soil Survey Office Leader.

- If the MLRA Soil Survey Office Leader accepts the edits/updates, the revised dataset is incorporated into the MLRA soil survey area-wide dataset.

- The MLRA Soil Survey Regional Office performs a quality assurance review of the revised spatial data.

- The State Soil Scientist determines if the revisions warrant placement into the Soil Data Warehouse.

- Based on the date and person making edits to the soils layer, the revised polygons are extracted and placed into the Soil Data Warehouse.  Currently, this step requires clipping and submitting the entire Non-MLRA Soil Survey Area to the Soil Data Warehouse.

- A pending modification to the current procedure will accept incremental updates at the polygon level.  It is expected that few surveys will need to be reposted in their entirety in this MLRA Soil Survey Area environment.  Historical record keeping is greatly reduced and processing more efficient.

- Metadata will track changes to this much smaller geographic area, potentially at the polygon level in a revised Soil Data Warehouse environment.

- The State Soil Scientist (or designee) notifies the appropriate area and field offices, and affected partner agencies of major revisions to the database, particularly if reclassification and update mapping affect USDA program implementation, such as changes to the hydric soils, highly erodible soils, and prime farmland lists.

- Attribute data (NASIS) needs to be current and included to successfully post the modifications.

610.07 Certification of Soils Data.

Data Certification is most commonly thought of as the process step whereby a State certifies and exports a dataset to the Soil Data Warehouse.  By certifying and exporting the data (attribute and spatial) the State is assuring that the dataset posted to the Soil Data Warehouse has passed quality control and quality assurance inspections and is suitable for use by the general public, and meets National Cooperative Soil Survey standards.  Progressive soil correlation, quality control, and quality assurance are essential and integral tools to certifying data.  These tools are used throughout the development of a soil survey product, including update products.

A very critical step in the data certification process is to ensure that all significant changes to any previously certified database are documented and recorded in the appropriate NASIS text field.  The reason for the change and what was actually changed must be properly recorded for future reference.  This is critical because it ensures that individuals performing subsequent quality control, quality assurance, or final export certification are made aware of the data revisions that warrant a review.  The following are appropriate NASIS tables for recording edits:

Legend Text – for edits to legend-level elements (e.g. area type, overlap acreage)

Legend Correlation – for any amendment to the correlation

Map Unit History – for recording any edits to the map unit symbol, name, or status

Map Unit Text – for any map unit-specific edits or comments

Data Mapunit Text – for recording any edits to specific State interpretations (e.g. IA CSR, VT Septic System) or changes in certification status

Component Text – for recording any edits to component-specific elements (e.g. composition percent, component name, slope, depth, drainage)

Horizon Text – for recording any edits to horizon data (e.g. textures, chemistry)

For each entry, the text note “Kind” is set to “edit notes”.  The “Category” column is populated with the name of the column that was edited.  When a dataset has passed a quality control review by the MLRA soil survey office, the data is certified as having passed a quality control review, and is now ready for a quality assurance review by the MO.  After the MO has performed a quality assurance review, and all needed edits have been completed, the data is certified as passing a quality assurance review and is now ready to be certified and exported by the State.

(a)	Guiding Principles of Data Certification.

  - The State is responsible for the quality of data certified and posted to the Soil Data Warehouse.

  - Prior to certification and posting to the Soil Data Warehouse all datasets must have passed a quality control review by the MLRA soil survey office and/or State and a quality assurance review from the MLRA (MO) Office.

  - Edit permissions must be limited to authorized individuals who have been delegated responsibility for populating, editing, and certifying data.

  - There must be consensus between the MO, State, and the MLRA soil survey office before edits privileges are given to an individual.

  - A SSURGO certified dataset designated for project update work must undergo evaluation before changes are made to the dataset.  Obvious errors such as omissions, accidental deletions, or typographical errors can be corrected without undergoing a formal evaluation.

  - All changes to a SSURGO certified dataset must be supported and documented in NASIS.  All changes to correlated component and map unit names must have concurrence from the MO office.

  - States can review, and initiate changes to, their State programmatic information but those changes must be coordinated with the MLRA soil survey office and the MO office.  They must also be supported and documented in NASIS.

(b)	Roles and Responsibilities for Data Certification.

  - The MLRA Soil Survey Regional Office (MO) is responsible for:

    - Coordinating with the State and MLRA soil survey office to provide training on using and editing soil survey databases and spatial data to ensure database and spatial integrity.

    - Managing group ownership, through coordination with the State and the MLRA soil survey office, to ensure that group membership is current, and that only authorized individuals are populating, editing, and certifying soil datasets.

    - Performing a quality assurance review of a soil dataset prior to certification and posting to the Soil Data Warehouse by the State; and assigning the quality assurance data certification levels in NASIS.

  - The State Office is responsible for:

    - The quality of data certified and posted to the Soil Data Warehouse.

    - Obtaining a quality assurance review from the responsible MO prior to certifying and exporting a dataset.

    - Certifying and exporting datasets to the Soil Data Warehouse, unless the State designates the MLRA soil survey office or the MO to perform this function.

    - Coordinating with the MO and the MLRA soil survey office to ensure that group membership for edit permissions are limited to authorized individuals delegated responsibility for populating, editing, or certifying data.

    - Reviewing, and initiating changes to their State programmatic information and ensuring those changes are coordinated with the MLRA soil survey office and the MO.

    - Confirming the certification levels for a dataset prior to export.

  - The MLRA Soil Survey Office (MLRA SSO) is responsible for:

    - Following national policy for conducting MLRA soil survey updates as outlined in the NSSH, including: evaluation procedures; formation of MLRA SSA technical and management teams; development of long-range plans, project plans, and annual plans; and conducting soil survey updates on an land resource unit, soil catena, or some geomorphic or geologic subset basis.

    - Performing an evaluation of the existing data prior to initiating update changes to a dataset.

    - Ensuring that all changes to a dataset are documented and properly recorded in NASIS.

    - Coordinating with the State and the MO to ensure that group membership for edit permissions is limited to authorized individuals delegated responsibility for populating, editing, or certifying data.

    - Coordinating with the State and the MO to obtain training for staff on populating and editing databases (attribute and spatial).

    - Ensuring that the datasets have passed quality control.

Exhibit 610-1 Sample Map Unit Evaluation Worksheet.

These questions and information should be answered and used for the evaluation of each map unit, the evaluation of the taxa used in the map unit name, and the evaluation of individual delineations of the map unit.  This information should be collected, analyzed and resulting information entered into the NASIS database (see NSSH 638) in the Legend Text or in the Mapunit Text table (as appropriate) under the appropriate map unit(s).  All notes entered into the Legend Text or the Mapunit Text should be populated using “Kind = “miscellaneous notes” and “Category = evaluation notes” and “Subcategory” as “spatial”, “attribute” or “interpretation”.  The national NASIS report named “MLRA - Evaluation notes for long range planning” is used to create the evaluation report.

Part A. Evaluation of the legend.

Summarize the evaluation information for the individual survey area:

How were the soil maps digitized?

What is the new base map for the update?

What is the new map scale?

What additional soil data have users requested?

What additional interpretations have users requested?

Briefly describe the investigative and laboratory support needed to provide the new data and interpretations.

Briefly describe how this survey will be improved by the update.

Briefly describe any publication plans in addition to the Web Soil Survey.

Part B. Evaluation of the map unit (subcategory “attribute”).

Probable map unit name if recorrelated

Do map unit names correspond with current NCSS and editorial standards?

Is the unit adequately described? If not, what is inadequate?

Does the map unit design meet current user needs within the MLRA?

Are limiting dissimilar soils named as minor map unit components in NASIS?

Is the amount and type of minor components consistent with NSSH guidelines?

Major uses of the map unit at the time it was correlated?

Major uses of the map unit in the current condition?

Are soil properties consistent with the needs of the current land use?

Are soil property entries to the NASIS database complete? (see NSSH 638 Exhibit 1)

Part C. Evaluation of the map unit components used to name the map unit (subcategory “attribute”).

Is the proper component kind value entered for this component?

Does the component name and/or taxonomic classification need to be updated?  If so, what is the proposed new name or taxonomic classification?

Do miscellaneous area names correspond with the approved list of miscellaneous areas?

Are component names properly entered with only the component name and in title case? (e.g., Jonus)

Are phase criteria properly entered in the local phase column?

Can the soil component be classified as presently described?  If no, why not?

Does the depth of typifying pedon meet current needs?

Does the series (taxa), as described, overlap with other series (taxa)?  If yes, describe how?

Does the typical pedon represent the map unit component?

Is there lab data for the series (taxa)?  If yes, how many, their locations and is it adequate?

Do the component properties concur with characterization data?

Is the representative pedon within the RIC of the OSD?  If not, why not?

Is the series consistent with parent material?

Is the series consistent with geomorphic landform?

Is the series consistent with geographic setting and the MLRA?

Part D. Evaluation of the map unit delineations (subcategory “spatial”).

Do soil lines fit major landform breaks?

Do lines correctly separate map units in the soil landform?

Is there a need to create new map units to delineate dissimilar soils?

Are dissimilar soils consistent with the map unit description?

Is the intensity of mapping suitable for the land use?

Does the series concept, as correlated, fit the map unit concept?

How was the mapping evaluated?

User comments?

Number of:   transects ________

field notes ________

descriptions ________

remapping ________ or

road checking line placement ________

Is there an exact join with surrounding surveys?

Is soil mapping consistently applied to landscapes across the major land resource area?

Does the use of features and symbols reflect current definitions and use standards on the Feature and Symbol Legend for Soil Survey, NRCS-SOI-37A?

Will this map unit require extensive revision (remapping)?

Part E. Evaluation of map unit interpretations (subcategory “interpretation”).

Address the interpretation issues within the survey manuscript.

Identify interpretation join issues of similar map units across survey boundaries.

Exhibit 610-2 Sample Evaluation Information for Long-Range Planning.

U.S. DEPARTMENT OF AGRICULTURE

NATURAL RESOURCES CONSERVATION SERVICE

MLRA - Evaluation Information for Long-Range Planning

Evaluation Notes for the Extensive revision Soil Survey of

Grand Forks County, North Dakota

Final Correlation Completed 02/1980

Total acres: 921700

Total mapunit numbers: 28

Total components: 152

County(s): Grand Forks

Scale: 1:20000

Initial field review date: 05/15/1960

Final field review date: 10/15/1979

Correlation date: 02/1980

Publications: Traditional Bound Manuscript : 05/15/1981

Land category: Other Non-Federal Land: 908133

Land category: Other Federal Land: 12361

Land category: Census Water: 1206

Prime farmland acres: 211017

Statewide important farmland acres: 13281

No local important farmland designated

No unique farmland designated

Not prime farmland acres: 114908

Legend evaluation notes:

interpretation: The survey has been reviewed and the information pertaining to the interpretations is addressed in this field.

spatial: The spatial database has been reviewed for this survey and this is the location to discuss those issues to be addressed.

attribute: The NASIS data for this legend has been reviewed and this particular field is used to identify any issues related to the attribute data.

__________________________________________________________________________________________________________________

|        |                                                   |                                                   |

|  Map   |                   Map unit name                   |             Mapunit evaluation notes              |

| symbol |                                                   |                                                   |

|________|___________________________________________________|___________________________________________________|

|        |                                                   |                                                   |

| 401    |Aberdeen-Nutley silty clays                        |attribute: Horizonation in NASIS DMU does not match|

|        |                                                   |Grand Forks TUD.  Aberdeen reference components    |

|        |                                                   |appear to be mispopulated.  The reference component|

|        |                                                   |is not similar to the manuscript below 97 cm. OSD  |

|        |                                                   |type is outside of MLRA 56.  MU composition has 55%|

|        |                                                   |Aberdeen in NASIS relative to 65% in pub.  NASIS   |

|        |                                                   |has inclusions of Exiline, Overly, and Great       |

|        |                                                   |Bend...pub only Exiline.  NASIS inclusions are     |

|        |                                                   |supported by the surrounding map units and         |

|        |                                                   |delineation placement. This unit occurs in similar |

|        |                                                   |areas to 091009.                                   |

|        |                                                   |                                                   |

|        |                                                   |spatial: Two delineations of 035401 appear to be   |

|        |                                                   |mapped out of place lower in the lake plain proper.|

|        |                                                   |Two delineations of 035401 appear to be mapped out |

|        |                                                   |of place lower in the lake plain proper. 035401 and|

|        |                                                   |091009 may deserve a field investigation to        |

|        |                                                   |determine if they can be combined into one unit and|

|        |                                                   |to document differences between these Aberdeen     |

|        |                                                   |units and the seemingly wetter units to the south. |

|        |                                                   |                                                   |

|        |                                                   |interpretation: Documentation in Richland county   |

|        |                                                   |(see map unit text for I250A) verifies SP drainage |

|        |                                                   |but this is out of the RIC for Aberdeen series. The|

|        |                                                   |interpretations have been compared from NASIS to   |

|        |                                                   |the manuscript and it is obvious there were some   |

|        |                                                   |overrides in the publication.                      |

|        |                                                   |                                                   |

MLRA - Evaluation Information for Long Range Planning

MLRA - Evaluation Information for Long Range Planning -- Continued

__________________________________________________________________________________________________________________

|        |                                                   |                                                   |

|  Map   |                   Map unit name                   |             Mapunit evaluation notes              |

| symbol |                                                   |                                                   |

|________|___________________________________________________|___________________________________________________|

|        |                                                   |                                                   |

| 64     |Antler silt loam                                   |interpretations: from review of MUD:               |

|        |                                                   |                                                   |

|        |                                                   |setting includes broad flats between old glacial   |

|        |                                                   |beaches                                            |

|        |                                                   |                                                   |

|        |                                                   |The TUD differs from the OSD in that the mantle is |

|        |                                                   |siltier                                            |

|        |                                                   |                                                   |

|        |                                                   |inclusions:                                        |

|        |                                                   |Antler, mod saline                                 |

|        |                                                   |Parnell                                            |

|        |                                                   |Tonka                                              |

|        |                                                   |areas with less clay (Gilby)                       |

|        |                                                   |areas that are mod well (Lankin)                   |

|        |                                                   |                                                   |

| 65     |Antler silty clay loam, saline                     |interpretations: from review of MUD:               |

|        |                                                   |                                                   |

|        |                                                   |setting includes broad flats between old glacial   |

|        |                                                   |beaches                                            |

|        |                                                   |                                                   |

|        |                                                   |The TUD differs from the OSD in that the mantle is |

|        |                                                   |siltier                                            |

|        |                                                   |                                                   |

|        |                                                   |inclusions:                                        |

|        |                                                   |Gilby                                              |

|        |                                                   |Ojata                                              |

|        |                                                   |Antler, nonsaline                                  |

|        |                                                   |Parnell                                            |

|        |                                                   |Tonka                                              |

|        |                                                   |                                                   |

| 171    |Antler-Mustinka silt loams, 0 to 2 percent slopes  |interpretations: from review of MUD:               |

|        |                                                   |                                                   |

|        |                                                   |setting includes areas between old glacial beaches |

|        |                                                   |                                                   |

|        |                                                   |The Antler TUD differs from the OSD in that the    |

|        |                                                   |mantle is siltier                                  |

|        |                                                   |The Mustinka was Tonka in the original publication |

|        |                                                   |                                                   |

|        |                                                   |inclusions:                                        |

|        |                                                   |Antler, mod saline                                 |

|        |                                                   |Parnell                                            |

|        |                                                   |                                                   |

| 70     |Antler-Mustinka silty clay loams, saline, 0 to 2   |interpretations: from review of published MUD:     |

|        | percent slopes                                    |                                                   |

|        |                                                   |setting includes broad flats between old glacial   |

|        |                                                   |beaches                                            |

|        |                                                   |                                                   |

|        |                                                   |The Antler TUD differs from the OSD in that the    |

|        |                                                   |mantle is siltier                                  |

|        |                                                   |Tonka is out of place, use Mustinka                |

|        |                                                   |                                                   |

|        |                                                   |inclusions:                                        |

|        |                                                   |Antler, slightly saline                            |

|        |                                                   |Gilby                                              |

|        |                                                   |Antler, nonsaline                                  |

|        |                                                   |Parnell                                            |

|        |                                                   |                                                   |

| 4      |Arveson loam                                       |interpretations: from review of MUD:               |

|        |                                                   |                                                   |

|        |                                                   |setting includes between old glacial beaches -     |

|        |                                                   |consider investigating, or a more thorough project |

|________|___________________________________________________|___________________________________________________|

Exhibit 610-3 Example of a Soil Survey Update Implementation Guide

Soil Survey Update Implementation Guide

March 2008

Overview

This implementation plan was developed to provide guidance to MLRA Soil Survey Offices in the Central Appalachian Mountains and Mid-Atlantic Coast Region in initiating the update process. It will assist MLRA Soil Survey Offices to become permanent clearinghouses for all soil-related data in their region. The long-term management of this data is vital to the Agency. The update approach for managing soil survey information here is separated into two, distinct phases: 1) Evaluation and Maintenance; and 2) Enhancement. The importance of a thorough evaluation of our existing product, establishing priorities, and developing long-range, annual, and specific project plans to address soil survey concerns are outlined in this document. NASIS activities are grouped into database integrity/management and soil properties. A discussion on the importance of increasing cooperator involvement and better communications between all soil survey entities are also included in this plan.  The primary guidance document for this plan is the National Soil Survey Handbook.

Introduction

The primary purpose of this document is to provide a framework to formalize discussion, input, and feedback from State Offices (SO), MLRA Soil Survey Offices (MLRA SSO), and Cooperators regarding priorities and structure of the reorganized soil survey program in MO-13 (Central Appalachian Mountains and Mid-Atlantic Region).

The reorganized soil survey program is an exciting opportunity for today’s generation of soil scientists to make significant improvements in the soil survey by utilizing new technology.  The current restructuring represents a major change in management of the soil survey program and how survey priorities are determined. This is a fundamental change from progressive soil survey and will reward proactive soil scientists with a sense of accomplishment and achievement. For example, instead of waiting 5 to 10 years for a survey to be published, improvements in the soil survey can be delivered to users via the Soil Data Mart or Web Soil Survey in a matter of weeks or months. The restructured soil survey program will allow individuals to emphasize the “science” in soil survey and refocus the program on details that were missed during the “project soil survey” era.

The Soil Survey Division has identified the following priorities which have a direct impact on the soil survey program in our region:

Enhance the Web Soil Survey (A continual process)

Implement new technology

Increase outreach and marketing.

Soil quality/health and dynamic soil properties

Support erosion models; water quality models

Watershed approach to applications

Cooperation and collaboration with partners

Addressing these activities will help us meet the Agency’s strategic goals and assist the MLRA SSOs in planning and management. Another objective of this document is to clarify the responsibilities of the MO, MLRA SSOs, and SOs and to discuss how these new roles will be implemented (responsibilities are detailed in the NSSH, Part 608). In the past, the MO was responsible for quality assurance and correlation. Although quality assurance remains with the MO, many of the correlation functions will be retained at the field level within the MLRA SSO. The MO views the MLRA SSOs as partners in achieving the final goal of delivering an accurate, reliable product to the Soil Data Mart. The MOs will assist the MLRA SSOs in delivering a high quality final product in an efficient manner.

The MO role is evolving into one that supports the states and MLRA SSOs by providing quality assurance through review of MLRA SSO operations, products, and accomplishments.  Also noted are:

developing processes, training, technical assistance

providing assistance and expertise in designing and completing projects

coordinating projects and issues among MLRAs  by facilitating meetings (e.g. committee meeting to resolve the use of phase terms among MLRAs)

maintaining NASIS data integrity

implementing standards in data population, map unit naming conventions, etc.

providing editorial assistance in publications, open record files, etc.

providing a clearing house for technical data (directory of PowerPoint presentations, photographs, etc.).

A major goal of restructuring the soil survey program is strengthening the relationships with our cooperators. The MO will explore ways to further the involvement of University, state and federal agencies in our program. As an important first step, MLRA SSOs should assemble a Technical Team and hold regular meetings to solicit cooperators’ input and determine survey priorities.

Through the course of the progressive soil survey program, soil scientists have and continue to collect a large amount of soil property and interpretive data. Although much of this information is available through published soil surveys and other sources, a considerable amount of valuable data is not available to the public. The result is that many soil scientists are not aware of technology advances or data collection projects that could improve their operations.

This lack of timely communication has been identified by the MO-13 leader as one of the major issues affecting the success of update soil surveys. The MO hopes to strengthen communication lines by hosting technical seminars and workshops.  Each MLRA SSO will be asked to contribute to these activities. Such actions should also enhance the soil survey program’s outreach and marketing activities.

For the purposes of this document, the restructured soil survey program can generally be broken into two broad phases:

1.  Evaluation and Maintenance of our current spatial and property data base; and,

2.  Enhancement of our survey for future users. Although much of our emphasis recently has been focused on the use of new technologies to improve our update soil survey; evaluation, maintenance, and enhancement should be viewed concurrently.

Initially, over half of a project office’s time should be spent maintaining and evaluating our current soil survey product. Management of the update survey will be through the MLRA SSO planning process, as outlined in the National Soil Survey Handbook (NSSH 608 and 610).  The planning process consists of developing long-range, annual, and project plans along with appropriate workload analyses.

Phase I:  Evaluation and Maintenance of Existing Soil Surveys
“A Seven Step Process”

This phase of the update soil survey program will focus on evaluating the status of our current survey, developing a list of soil survey concerns, and maintaining existing survey data. These projects will have an immediate impact on soil survey users via the Web Soil Survey. Items emphasized in this phase will be evaluation of subset legends, map unit geographic distribution, and minor spatial changes for joining. Also discussed are issues related to Benchmark soils, OSD revisions, Taxonomy review, NASIS legend management, soil properties, and organization of existing data.

## Step One:  The Initial Evaluation

A.  The Legend

Our current subset legends were developed over two generations of county soil survey correlations. This has resulted in inconsistencies in naming similar landscapes in adjacent surveys.  Many inconsistencies in these legends can be resolved with a comprehensive review of MLRA subset legends.

The MO recommends that all MLRA Soil Survey Leaders undertake a thorough review of their subset legends to identify problem map units, landscapes, or data. This evaluation will create an inventory of “soil survey issues” that will later be prioritized and addressed via project plans.

For example, a review of the legends in MLRA-126 identified the need for update work in several “pre-taxonomy surveys”. The project office developed a project plan and set goals for their work in 2008.  The update survey was improved by correlating by physiographic areas.

Other examples of legend issues needing evaluation include:

- use of series that are out-date or have had classification changes

- series that have had conceptual changes

- assigning soil series to specific landscapes

- undifferentiated map units that could be converted to better interpretive map units

- establishing new series vs. phasing existing series

- consistent use of miscellaneous areas

- consistent use of the eroded phase

- consistent use of conventional and ad hoc symbols

- consistent use of slopes groups within a MLRA

- consistent use of map unit symbols

- documentation of all changes in NASIS and LIMS by organizing all Lab data

Correlation includes not only the map unit name but also the map unit composition and data. The legend evaluation should also review which minor map unit components are assigned to a map unit. In some instances, similar map units in adjoining counties have different components because different similar soil criteria were used or new series were established since correlation of one of the counties. The number of data map unit components also needs to be evaluated. Care should be taken not to add redundant components to the map unit that do not improve the map units’ interpretive capability. Consistent similar soil criteria will need to be established by MLRA.

The MO also supports facilitating consistent naming conventions within and among MLRAs. Although the NSSH gives guidance for naming map units, in some cases, clarification is needed. Most routine correlation amendments will be managed via populating the database with the map unit history notes and running the appropriate reports. The MO plans on establishing regional committees to make recommendations related to map unit naming conventions, use of ad hoc/spot symbols, and similar and dissimilar soils.

B.  Soil Geography

Along with the legend evaluation, the MO encourages MLRA SSOs to undertake a systematic evaluation of the extent and location of subset map units using SSURGO.

Such a review may highlight trends, anomalies, landform/soil correlations, or other issues that may impact the validity of map units. It is recommended this review be done by physiographic area.

C.  Cultural and Ad hoc Symbols

It is recommended that each MLRA SSO evaluate the NRCS-SOI-37A for each subset (SSURGO and published) and a standard set of symbols and definitions be developed for the MLRA. The goal is to use spot symbols in a consistent manner throughout the MLRA, taking into consideration past use, map unit minor components, etc.

D.  Spatial Data

Our SSURGO certified soil survey is an established product that has specific development protocols.  The MO discourages any project that emphasizes the revision of SSURGO using traditional survey procedures. The MO will require a cost/benefit analysis before approving an update project relying on traditional methods. Cost-effective and efficient soil landscape modeling techniques are or will be available to assist in making necessary changes. This philosophy could be modified for areas of small extent with serious problems with the existing mapping (e.g. watershed project). Any project requiring extensive line change should have MO review and the appropriate State Soil Scientist approval.

The MO concurs with the NSSH and strongly supports creating the best join possible among subsets and encourages MLRA SSOs to include such work in their long-range plan. Ultimately a seamless join would involve matching landscapes, map unit names, and data map units along subset boundaries. This perfect join may require substantial field and data base work. However, during the interim, improving the join by any means possible (matching line work, revising map unit names, utilizing similar component properties) is encouraged as a first step. An improved join would enhance GIS products and reduce interpretive discrepancies among subsets. Creating this join is a continuation of the of the legend evaluation process and may identify issues needing further evaluation.

E.  Evaluation of SSURGO developed from Topographic Base Maps (no photo image)

In the initial development of SSURGO for subsets in the late 1990s, a limited number of counties lacked orthophoto coverage. Topographic maps were used as a base map in lieu of photo image base. The MO recommends that MLRA SSOs evaluate the line work of these SSURGO subsets and make appropriate recommendations.

Step Two:  The Benchmark Soil Review

Review and evaluation of Benchmark soils is an Agency priority. Guidance has been provided by the NSSC on processes to review the current Benchmark soil list (issue paper, Tom Reedy and others). The NCSS has provided excellent guidance in reviewing Benchmark soils.  Most evaluations will extend the concept of benchmark soils to the landscape catena and will include comprehensive data mining to compile information related to the benchmark and associated soils.

The MO recommends each MLRA SSO evaluate their current Benchmark soils and make recommendations for changes. The MO will coordinate efforts among MLRA SSOs. This review should include an evaluation of a “data completeness index” as described by the NSSC.  The data completeness index (DCI) was developed after pedon data in the NSSL database were evaluated to determine the quantity of data available for each pedon.  Contact the National Leader for Soil Survey Research and Laboratory at the NSSC for more information on the data completeness index.

Step Three:  The Official Series Descriptions (OSD) Review

Revision and maintenance of OSDs is primarily the responsibility of MLRA SSOs. We urge all MLRA SSOs to initiate a plan to systematically review and revise the OSDs in their MLRA(s). This review should prioritize the OSDs and work should begin on benchmark and extensive series or soils involved in on-going MLRA work. It is recommended that each MLRA SSO develop an OSD maintenance plan as part of their long-range plan. This should include the review of a specific number of series annually. MO-13 will assign series responsibility to individual MLRA SSOs.

At a minimum, the following items should be addressed (see NSSH for additional guidance):

- determine if the pedon is representative for that series (high importance)

- review the Range in Characteristics

- review the Competing Series (update this section in the competing series also)

- review the Associated Series (update this section in the associated series also)

- review the Geographic Setting

- review Remarks Section; add statements concerning any diagnostic features

- update to 2 meters (if possible)

- convert to metric

The national OSDCheck Program will be used in each SSO. The following procedure is suggested for revising OSDs:

- SSO submits draft changes and justification/documentation to review groups (as appropriate) and the MO. Any change in OSD classification, location, or significant change in morphology needs to be reviewed by a knowledgeable peer group.

- SSO incorporates final changes and submits to MO; along with additions to the “.a” file.

- MO submits the OSD file to the national Soil Classification File and maintains the “.a” file locally.

At this time the MO will continue to maintain the OSD and “.a” files. These files can be checked out by MLRA SSOs for series they are working with. A link between the OSD and series property data in NASIS is eventually planned. Until this link is established, a MO-wide decision needs to be made about the amount of soil property information that will be included and maintained in the OSD (versus maintained in NASIS).

The MO supports the development of Soil Monographs as both an outreach activity and as a means of summarizing available property, laboratory, and landscape data.

Step Four:  Applying Soil Taxonomy

MLRA Soil Survey Offices have the responsibility for evaluating Soil Taxonomy. We realize that Soil Taxonomy is fairly stable in the Appalachian Region; however, MLRA SSOs need to identify any issues affecting Soil Taxonomy and help collect appropriate documentation to support revisions. Several issues affecting soils in the MO have been identified, including:

- recognizing anthropogenic induced change in soils

  - erosion

  - mine-land reclamation

  - drainage

  - Extent and spatial variation of compaction in mined soils

- CEC activity class

- soil moisture and temperature regimes

- horizon criteria; including the usefulness of subgroups

Step Five:  The Database

Database activities have been separated into two distinct categories:

- Integrity and management of site and legend objects; and,

- Properties and interpretations (the update of soil property and interpretive data).

A.  Integrity and Management of Site and Legend Objects

Management of the NASIS database MUST be coordinated with state database managers.

Potential issues:

- Group membership.

- Legend management and group organization.

- MLRA vs. Non-MLRA legends—Presently it is a challenge managing groups when our delivery mechanism (Non-MLRA) is different than our management mechanism (MLRA). This results in potential security issues when adjacent MLRA SSO leaders are included in groups to allow permissions for soil survey areas that are along MLRA management area boundaries. To help resolve these issues, MLRA SSOs managing an MLRA Legend need to populate and maintain a set of Non-MLRA soil survey area overlap tables.

- Management of MLRAs 124-126 North and South.  A plan needs to be developed that documents the separation of 124/126 north and south and incorporate these changes into NASIS.

- Effective organization of reports and queries – This task is slated for the MO data base manager.

- Report writing assistance.

- Site data/site data quality – The MO recommends resources be allocated towards an effort to populate archived site data (OSDs, lab, typical pedon, and other pedon descriptions, transects, field notes) in the NASIS database. There is also a need to evaluate the quality of the site data currently in the NASIS and LIMS databases. (duplicate pedons entered, data transcription errors, etc.)

- Automate the population of side records – Several stand alone data sets exist that need to be updated with changes in NASIS. Methods of updating these data sets automatically will be evaluated.

B.  Database – Properties, Qualities, and Interpretations

The preliminary objective in data evaluation and maintenance is maintaining our existing data, improving consistency among similar soils, and eliminating discrepancy among adjacent counties. Projects to enhance the data base through survey projects will be discussed later.

- Typical or modal pedons. The primary purpose of modal pedons in NASIS is to structure the associated chemical and physical data and provide depths and thicknesses for interpretations. Modal pedons selected to represent both major and minor components in data map units need review to ensure they represent the component in that specific map unit and/or landscape. Modal pedons should be evaluated and chosen based on natural physiographic units. In some cases little significant difference in major soil properties occurs among physiographic units and the similar modal pedons can be used on several surfaces (e.g. use of the same modal pedon.  In many cases, this review can be combined with evaluation of the OSDs (see above). A concern exists between interpretations presently being run on “thickest” layer and use of soil horizons in NASIS. The MO recommends that layers be replaced with significant horizons (i.e. separate horizons with significant differences and combine horizons with minor difference, e.g. color change).

- Soil property data for DMUs throughout the MO all have been certified and meet the minimum data requirements of National Bulletin 435-5-7. However, there are inconsistencies in data population standards, guides, use of calculations, data validations, etc. The MO recommends the next step in data population involve evaluation of population standards throughout the MLRAs.

Better data population of primary soil properties will lead to better interpretations for all users. The evaluation of data will require:

agreement and coordination of criteria among MLRAs and states

deriving data from soil properties where possible (e.g. derive K from soil properties).

The following steps are envisioned:

The MO will work with MLRA SSOs to evaluate standard calculations and algorithms and make recommendations for their use (i.e. populate CEC from algorithm vs. state criteria).

Existing Data Guides will be reviewed and summarized (e.g. AWC reduction for salinity and stones; SD’s K factor guide). A formal revision and distribution procedure will be developed (similar to the present “Data Population Notes”) and the MO will develop a web page to provide easy access to all guides, criteria, etc.

Data population criteria will be evaluated to facilitate population of:

- Organic horizons

- Cd horizons; Cr and R layers

- Miscellaneous land types

- Other

Criteria and reports will be developed or reviewed to derive or generate interpretations from soil data. This will impact interpretations such as:

- Land capability class

- Forage suitability groups

- Important and Prime farmland

- Productivity Indexes

- Other

“Local and State” data and interpretive criteria will need to be identified to avoid impacting these data elements. The MO will develop a standard data validation routine consisting of existing reports and validations to run before any SSURGO data downloads. Work is being done on the national level to facilitate quality control of SSURGO downloads.

Step Six:  Organization of Existing Data

The establishment of MLRA SSOs in the restructured soil survey program has created the opportunity for these offices to become clearinghouses for all soil survey information for their assigned MLRAs.  This can lead to the consolidation and compilation of soil survey data currently housed at various locations. Centralizing this information will leave a legacy the next generation of soil scientists will appreciate. This data will also make positive contributions and improve the efficiency of projects.

The MO recommends data libraries are established for:

- County subset 30 year records

- Map unit transects and notes

- Series descriptions

- OSD files

- Survey evaluations

- Laboratory data

- Water table data

- Old soil survey reports

- Photographs

- Geology reports

- Research reports

- Other

It is important to maintain an effective record keeping system. The MLRA SSOs have become permanently located and will need to archive files for future reference.  Record keeping systems will need to correspond to the Records Guide GM-120-408.

Step Seven:  Our Family of Maps – GIS Applications

Along with compiling existing hard copy data, an inventory of existing digital/GIS data will be essential for these new survey offices. The MO will provide a digital “basic cartographic set” which includes SSURGO, roads, hydrography, geology,  strongly recommends that each MLRA SSO query GIS sources to develop an inventory of existing data such as ground water, aquifers, land use, geology, STATSGO, etc. Because digital data files can be large, many SOs have developed protocol for storage. It is important that a formal structure is used so data can be easily accessed, updated, protected.

The MO recommends that a series of resource maps be developed for each MLRA. These maps could highlight conservation or resource issues such as:

- water erosion

- major soils

- aquifer

- drought potential

- poultry composting

Phase II: Soil Survey Enhancement
“A Six Step Process”

Step One:  The Planning Process

Improving the current soil survey spatial, property, and interpretive data in an efficient and cost effective manner is the main goal of the update soil survey. Most update work will be centered on the planning process as outlined in the NSSH part 608. Priorities will be determined by input at local technical team meetings and national, SO, MO, and MLRA SSO objectives. Detailed project plans will describe objectives, procedures and impacts on the survey. The MO will provide any needed assistance in the planning process.

The soil survey update planning process, as outlined in the NSSH, consists of the long-range, annual, and project plans. MO-13 would like to add an MLRA SSO annual status report that would summarize achievements for the year and be a focal point for quality assurance activities. All of these documents contribute toward organizing, prioritizing, and documenting survey activities. These plans, field visit reports, and associated final reports will constitute the long-term record of the survey office (in lieu of field review reports). They should be maintained in an “open record” format, accessible, and well organized.

Although the writing of technical documents to guide the management of a survey office may seem like the antithesis of traditional field soil survey activities, planning has always been a part of the NSSH guidelines.

When one considers that over $1 million dollars of public funds can easily be expended to support a single MLRA SSO for 5 years, well-designed and documented work plans seem a minor but essential requisite.

A.  Long-Range Plan

The Long-Range Plan should address activities of the MLRA SSO for up to about a five year period.  It should identify equipment, personnel, and other needs over the plan’s time span.  The Long-Range Plan should include a ”Needs” list which is an inventory of needs, issues, and concerns identified by MLRA SSO through the evaluation process completed in Phase I.  Survey concerns should be sorted by topic (e.g. correlation needs, classification issues, soil-landscape issues, etc.). The Needs list is a dynamic document that will be revised as update work progresses.   See NSSH Part 608 Exhibit 608-3.

Prioritizing Projects

Although seemingly straightforward, prioritizing projects is a delicate balancing of local concerns with national, state, and MO issues. The objective is to create an efficient survey program by “weaving” together a variety of projects with various timeframes that will efficiently utilize SSO staff, account for adverse weather, and allow annual accomplishments to be reported. Prioritizing projects must consider benefits/cost ratios, easily accomplished projects, importance, acres impacted, staff capabilities, etc. The NSSH recommends analyzing the cost of the revision (project) in comparison to the anticipated gain of additional information.

The Needs list, developed in the evaluation phase of the update, along with input from Technical Team meetings and cooperators will help determine local priorities. These local issues will be merged with national office, MO, and SO priorities identified at regional and state work planning conferences to create a list of priorities that will be addressed by the soil survey long-range plan. The State Soil Scientist and MO Leader should approve the issues included in the soil survey long-range plan. These priorities will be presented to the regional Board of Directors for review and comment.

Many states have developed criteria for ranking update and maintenance work. One approach is to numerically rank projects based on the following criteria:

Scientific merit

External merit

Internal merit

Financial/Partnership inputs

Efficiency

County soil survey deficiencies

There is merit to implementing some type of process to evaluate the need and importance of individual projects, especially projects that will require substantial resources. The MO will investigate ranking projects to determine priorities further. MLRA SSOs are urged to review these ranking procedures to assure they are addressing important issues. In the mean-time, we will rely on peer review comments to evaluate the significance of projects.

The Long-Range Plan should also include a general workload analyses that briefly describes how staff time is allocated. The Long-Range Plan should be approved and signed by the SSS and MO Leader. The plan should be updated annually and submitted to the appropriate supervisor by early September.

B.  Project Plan (See NSSH Part 608, Exhibit 608-5)

Project plans discuss a project in detail; including objectives, timeframe, reportable items, products, etc. All project plans should be peer-reviewed and approved by the SSS and MO Leader. They should be coordinated with other MLRA SSOs as appropriate. As with the other types of plans, a formal file system should be created that includes the project plan, field visits, correspondence, final report, and future work needs. All project plans should be dated and numbered systematically. They should include provisions for quality control/assurance. Project plans need to be approved and signed by the SSS and MO Leader. They may be submitted at any time.

This plan could easily be modified for routine soil survey. Some projects will lend themselves to publications (e.g. Soil Survey Horizons, NSSC Newsletter) or presentations at professional meetings (oral or poster). Where appropriate, the MO recommends project plans be implemented with publication as a consideration.

Some projects, such as evaluating dynamic soil properties may be broader than individual MLRAs and may originate at State Offices or the MO.

C.  Annual Plan of Operations (See NSSH Part 608, Exhibit 608-6)

The Annual Plan of operations outlines activity for the current year. It identifies reportable items, current priority projects, requests for assistance, and needed resources. It includes a workload analyses, detailing project time, training, annual leave, etc. The Annual Plan is approved and signed by the SSS and/or MO Leader. The plan should be developed annually and submitted to the appropriate supervisor by early September.

D.  Annual Status Report

The MO requests a summary report from each MLRA SSO annually. The objective of this document is not to record reportable items but rather a summary of activities, accomplishments, and suggestions for improvements. These reports will allow the MO to consolidate quality assurance activities. These reports should be submitted to the SSS and/or MLRA Leader by the end of December.

## Step Two:  Revising Spatial Data

Results from projects may lead to the need to revise spatial data. Spatial revisions can be updated by traditional means, GIS Assisted Editing, and GIS derived Soil-Landscape Modeling. The MO does not support traditional means of updating soil survey unless the project is approved by the SO and the Soil Survey Division Director. GIS Assisted Editing relies on the use of simple GIS tools (ArcMap) to display SSURGO, DEMs, etc. to assist implementing map unit design changes.

For example, GIS Assisted mapping has been used to:

separate slope breaks (e.g. a 6 to15% unit into 6-9% and 9 to 15% units)

delineate eroded, wooded, and dissected areas

delineate consistent fluvial units between subsets (flooding duration and frequency).

Sophisticated Soil-Landscape Modeling is the probable future of any terrain analyses, including soil survey. The implementation of this technology can be considered the 3rd generation of soil survey. Besides delineating soil boundaries, Landscape Modeling has potential to statistically evaluate soil variability and correlate soil properties to landscape position. It may provide resource maps for precision farming or precision conservation that could be aggregated into Order 2 soil surveys.

Step Three:  Revising Existing Soil Properties, Qualities, Interpretations

Soil survey projects designed to revise and quantify existing soil properties will allow representative data values and ranges to be determined statistically, with confidence levels assigned. This will assist in risk analyses and understanding specific property variance.

For example, assigning confidence levels to our Ksat values may persuade designers of septic system to consider other alternatives. Evaluating data elements should be prioritized by importance, such as data elements (OM, pH, CEC, AWC, PSA, dB, Ksat). Evaluating existing characterization and other sources of hard data (university/ARS research), calculating “data completeness indexes” and identifying data voids are all part of the evaluation process. Once data voids or needs are identified, field data collection, sampling, Amoozemeter, EM-38, and Hach kits all can be utilized to quantify properties. Work should initiate on benchmark soils or suites of similar soils (benchmark landscapes).

Step Four:  New Data Elements

Several new data soil properties, not currently supported in NASIS and related to dynamic soil properties or geochemical data, are being considered for data evaluation. These properties, such as infiltration, POM, aggregate stability, and trace metals will address emerging resource concerns. Soil Quality Specialists in the Midwest are developing multi-state plans to implement the collection of dynamic soil properties and geochemical data into routine soil survey.

Step Five:  New Interpretations

Several recommendations for new or revised interpretations are being considered by the MO. MLRA SSOs will be requested to assist in testing any new or revised reports. Examples include: source of secondary road material, compaction rating for mining and forestry, animal waste, septic systems, Ksat calculations, range PIs, road construction/reclamation on steep areas, and wildlife.

Step Six:  Miscellaneous Issues

Several miscellaneous issues need additional consideration:

- Managing and revising STATSGO

- Effective outreach and marketing

- 01 activities

- Training new soil scientists

- Sharing job aids

- Establishing long-term monitoring sites

- MO business plan  (Annual)